## Sheet1
Task-ID | Task | Sub-Tasks | Assigned Team Member | Priority | Deadline
1 | Venue Setup | 1. Secure venue | Logistics Team | High | 1st Week
2. Organize seating and tables
3. Arrange internet connection and power supply
4. Setup audio-visual equipment
2 | Sponsor & Mentor Coordination | 1. Contact sponsors for funding | Partnership Team | High | 1st Week
2. Confirm mentor availability
3. Organize mentor briefing session
3 | Participant Management | 1. Open registration | Event Management Team | Medium | 2nd Week
2. Send confirmations
3. Prepare welcome kits and badges
4 | Marketing & Promotion | 1. Design promotional materials | Marketing Team | Medium | 2nd Week
2. Launch social media campaigns
3. Send out press releases
5 | Workshop Preparation | 1. Confirm workshop topics | Content Team | High | 3rd Week
2. Coordinate with speakers
3. Prepare workshop materials
6 | Event Day Management | 1. Organize check-in process | Operations Team | High | Event Day
2. Assign volunteers
3. Monitor schedule adherence
4. Address on-site issues